## Sheet1
Env | Sr no | Activities | status | Finish date | Remark
|  | Repo creation for IS |  |  | dependency on helm charts to update files in repo
Variable group creation
Artifact feed creation environment specific
Dev | 1 | Helm chart creation | completed | 2024-05-31 | Submitted to guru for review once we get finished
| 2 | Python script creation 1) BarUrls scripts 2) Encoding and chart update script | in progress |  | Script for Barfile url script is completed second one in progress
| 3 | Helm and oc cli installation |  | 2024-06-03
|  | further dependency identification |  |  | just for buffer
| 4 | pipeline creation for manifest deployment |  |  | api server url and tokken required
| 5 | pipeline modification for build bar file |  |  | Use of existing code and remove deployment code from template
| 6 | Deploy pipeline creation
QA | 1 | Helm chart creation
| 2 | Python script creation 1) BarUrls scripts 2) Encoding and chart update script | Reuse dev script
| 3 | further dependency identification
| 4 | pipeline creation for manifest deployment
| 5 | pipeline modification for build bar file |  |  | Use of existing code and remove deployment code from template
| 6 | Deploy pipeline creation
PROD | 1 | Helm chart creation
| 2 | Python script creation 1) BarUrls scripts 2) Encoding and chart update script | Reuse dev script
| 3 | further dependency identification
| 4 | pipeline creation for manifest deployment
| 5 | pipeline modification for build bar file |  |  | Use of existing code and remove deployment code from template
| 6 | Deploy pipeline creation