## Sheet1
start date | activity
2023-09-11 | introduction of exiting flow
2023-10-06 | received vm
2023-10-09 | gitlab runner installation
2023-10-17 | testing fail while building war file
2023-10-18 | dependency issue in MS
2023-10-23 | received updated ip details of environment
2023-11-01 | API gateway prod urls present needed to update with qa
2023-11-02 | updated java code with correct details
2023-11-06 | dependency issue in react code
2023-11-07 | 2-3 errors in react code
2023-11-10 | sent url list need to be add in java and react code
2023-11-15 | Came to know in QA there is no API gateway and all individual MS urls are hard coded in react code confirmed from Ravi and srikant